## To do
Timeline
✓ | Date | Task : mechanical | Task : IT | Milestone
FALSE | 2018-07-11 |  | Finalisation des documents du design control | RENDU P1 : - TDR “Requirements of System” - TDR “Architecture of System” - SRS of R1 - SRS of R2 - TP for R1 - TP for R2 - Project planning - Project budget - Team organizational chart
FALSE | 14/11/2018 | Robot 3D conception | Plan the schematic of Xe 1.0 Begin the work in simulation the enviroment and the robot on V-REP Begin the study in image processing |  | MODIF: présenter le planning pour permettre la libilité, en gantt comme ca:
MODIF: bien discerner ce qui est du boulot, qui dure dans le temps, et ce qui est un *livrable*, qui doit être délivré à une date donné. Avec un livrable, on a l'avantage de pouvoir dire "PASS / FAIL". Demandez vous toujours "qu'est ce qui me permettra de cocher la case "A", c'est quoi ma condition ?
MODIF: ensuite le planning sera tracké principalement sur les livrables. Essayer d'en mettre en moyenne 1 par mois pour saucissoner le projet et voir s'il dérive rapidement.
MODIF: ca parle pas du hard: a quel moment on a les différentes version de robots opérationnelles mécaniquement (a part la rolling base qui est définie la)
FALSE | 28/11/2018 | Robot 3D conception | Have the first circuit schematic ready for Xe 1.0 |  | SUPER MODIF: le planning ne va pas jusqu’à la coupe !!!
FALSE | 2018-05-12 | Robot 3D conception Electrical design (sensors, control system with IT group) | Set up the circuit on a solderless breadboard Implement PID on Xe 1.0 |  | Question technique, pourquoi il y a besoin d'une breadboard ?
FALSE | 2018-12-12 | Electrical design | Implement PID on Xe 1.0
FALSE | 19/12/2018 | 3D printing Completing control system with IT group | Implement PID on Xe 1.0 Get the simulation enviroment ready on V-REP Begin the optimation algorithm on the simulation
FALSE | 2019-09-01 | Game table construction | Game table construction | MODIF: par exemple ici il y a un livrable clair !
FALSE | 16/01/2019 |  | Info : Have some modules ready to reduce the complexity of the wire connection Begin the study of tranmission data between Arduino and Rasberry Pi Image processing is ready to launch
FALSE | 23/01/2019 | Finalizing rolling base Ready for the test R1 | Finalizing rolling base Ready for the test R1 | Rolling base finalized
| 30/01/2019 |  | Test movement Code improvement
FALSE | 2019-06-02 |  | Code improvement
TRUE | 13/02/2019 |  | Xe 1.0 survive the test R1 | Target date for test R1
FALSE | 20/02/2019 | Conception of actuators | Submit the test R1 Communication between the camera and the robot
FALSE | 27/02/2019 (Winter vacation) |  |  | Due date for test R1
FALSE | 2019-06-03 | Actuator's control system | Be able to trasmit perfectly data between the camera and the robot Get the algorithm, the transmission technique and image processing working together
FALSE | 13/03/2019 | Begin the test R2 | Begin the test R2 Code improvement
FALSE | 20/03/2019 | Finalization of actuators | Code improvement
FALSE | 27/03/2019 | Actuators assembly | Code improvement
FALSE | 03/04/2019(Présentation de PA) |  | Code improvement
FALSE | 2019-10-04 |  | Pass the test and release Xe 2.0 | Target date for test R2
FALSE | 17/04/2019 |  | Submit the test R2
FALSE | 24/04/2019 |  |  | Due date for test R2