## Feuille 1
The passing of R3 is validated by a complete test of the robot, detailled hereunder. Unless specified exception, all steps shall be repeated successfully 10 times in a row to be considered PASS. Several requirements of the SRS R3 can be validated during this global complex test (in some cases, it would even be absurd or unnecessarily complicated to validate them separately) In all the document, "PL" stands for "purposeless"
MODIF: cf mon autre remarque, faire officiellement 2 TP et dire quels REQU chacun permet de vérifier.
| Robot mission | 2,7,12-13, 22-39
Step | Actions | Means of measurement | Expected outcome | Tested requirement(s) | PASS/FAIL
Programming of the trajectory | Store a chain of 6 waypoints, randomly placed on the match table, but distant enough from any obstacle, as the robot is not yet supposed to detect any obstacle (the point shall be adequate, see SRS R1). It is also possible to store a set of 10 chains of 6 waypoints (to avoid reprogramming the robot 10 times), then this step shall be done only once. The points shall be chosen randomly for every time. | PL | PL | PL | PL | MODIF: les waypoints doivent être différents à chaque test MODIF: si vous considéréz que le robot, a ce stade, aura sa detcetion d'obstacle, mais risque de détecter les obstacles de la table, il faur le préciser dans la spec, ou alors préciser qu'il n'a pas de calcul d'évitement d'obstacles de table connus. il faut le dire dans la spec. et du coup c'est necssaire dans la spec R2
Piece of Velcro | Stick an object of mass >= 300g with Velcro on the top of the beacon of the robot. This step is done only once (not ten times). However it is tolerated to fix again the object after every match, if it has not completely fallen during the match. | PL | At the end of every "match", the piece of Velcro is still sticking to the beacon. | REQU 17 REQU 21 | ?
Batteries | Equip the robot with a fully charged battery. This battery can be replaced by a charged battery only once during all the test. | PL | The capacity of the two batteries is sufficient for the robot to pass all the test. | REQU 24 | ?
Installation of the robot | Place all necessary elements (robot, wooden blocks, etc.) next to the match table. Measure the duration of the installation until the robot is correctly placed in its starting zone and all annex elements are removed from the table. The robot shall be placed at rest (not deployed). | Chronometer (smartphone) | Duration <= 3min | REQU 23 REQU 2 | ?
Starting position | Measure the initial position (x, y) of the robot. This position is given as the middle of the axis of the motor wheels of the robot. | Tape measure Eventually, erasable pen to notch the initial position on the table | PL | PL | PL
Starting the robot | Pull the string. Measure the time taken by the robot to start moving. | Chronometer (smartphone) | The robot starts in <= 1s | REQU 7 | ? | MODIF: celui la on peut le mettre dans le "one time test"
Stopping the robot | The robot moves to all 6 waypoints in the given order, and gets back to its starting position. After complete stop, it emits a recordable signal (sound or light) and does not move further. Measure the duration between the pull of the string and the final signal. | Chronometer (smartphone) | Duration <= 100s | REQU 13 | ? | MODIF: it emits a recordable signal (sound or light) and does not move further. Je ne crois pas que ca soit dans votre SRS Il faut ajouter la précision à laquelle il doit passer à chaque waypoint (qui doit venir de la spec)
Precision of the trajectory | Measure the final position (x, y) of the robot. This position is given as the middle of the axis of the motor wheels of the robot. | Tape measure, compass | The final position is contained within a 20cm diameter circle, whose center is the initial position of the robot. | REQU 25 & 26 | ?
Fiability | All steps hereabove are repeated successfully 10 times in a row. | PL | PL | Final test R1 | ?